## Project Tracker
Programming Project Activity and Effort Tracker
Project | Assigned To | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | List of Specific Task Completed | Percentage of Ownership of Task
Phase 5 | Jocelyn Frechette | 2023-12-07 | 2023-12-07 |  | 5 |  | Initial Design | 33
Phase 5 | Michael Burton | 2023-12-07 | 2023-12-07 |  | 5 |  | Initial Design | 33
Phase 5 | Jesse Haynes- Lewis | 2023-12-07 | 2023-12-07 |  | 5 |  | Initial Design | 33
Phase 5 | Jocelyn Frechette | 2023-12-08 | 2023-12-09 |  | 4 |  | Debug/Test | 33
Phase 5 | Michael Burton | 2023-12-08 | 2023-12-08 |  | 4 |  | Debug/Test | 33
Phase 5 | Jesse Haynes- Lewis | 2023-12-09 | 2023-12-09 |  | 3 |  | Debug/Test | 33
Phase 5 | Jocelyn Frechette | 2023-12-13 | 2023-12-13 |  | 3.5 |  | Documentation | 33
Phase 5 | Michael Burton | 2023-12-13 | 2023-12-13 |  | 3 |  | Documentation
Phase 5 | Jesse Haynes- Lewis | 2023-12-13 | 2023-12-13 |  | 3 |  | Documentation