## Project Tracker
Programming Project Activity and Effort Tracker
Project | Assigned To | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | List of Specific Task Completed | Percentage of Ownership of Task
Phase 4 | Jocelyn Frechette | 2023-11-06 | 2023-11-06 |  | 1 |  | Initial Design | 33
Phase 4 | Michael Burton | 2023-11-06 | 2023-11-06 |  | 1 |  | Initial Design | 33
Phase 4 | Jesse Hayes- Lewis | 2023-11-06 | 2023-11-06 |  | 1 |  | Initial Design | 33
Phase 4 | Michael Burton | 2023-11-10 | 2023-11-10 |  | 2 |  | Timers and State Machine | 50
Phase 4 | Jocelyn Frechette | 2023-11-10 | 2023-11-10 |  | 2 |  | Timers and Introduciton of Loss | 50
Phase 4 | Jocelyn Frechette | 2023-11-11 | 2023-11-12 |  | 3 |  | Documentation | 33
Phase 4 | Michael Burton | 2023-11-12 | 2023-11-12 |  |  |  | Documentation | 33
Phase 4 | Jesse Hayes- Lewis | 2023-11-12 | 2023-11-12 |  |  |  | Documentation | 33